## Dashboard
QC SCENARIO PLANNING DASHBOARD - MULTI-RESOURCE
KEY METRICS OVERVIEW
Total Team Size | 5 | members
Total Weekly Capacity | 160 | hours
Average Hourly Rate | 60 | $
Active Projects | 3 | projects
Total Projects Hours | 71 | hours
Active Tasks | 2 | tasks
Total Task Hours | 240 | hours
Avg Project Completion | 54.93% | %
Avg Task Completion | 84.38% | %
RESOURCE UTILIZATION ANALYSIS | [7 empty] | PROJECT MULTI-RESOURCE BREAKDOWN
Resource | Level | Weekly Capacity | Project Hours | Active Task Hrs | Total Allocated | Utilization % |  | Project | Total Hours | Completion % | Status
Basel | Senior | 40 | 0 | 0 | 0 | 0% |  | CST | 71 | 64.79% | At Risk
Belal | Mid | 40 | 0 | 8 | 8 | 20% |  | FRA | 0 | 0% | No Tasks
Mahmoud | Junior | 40 | 0 | 3 | 3 | 7.5% |  | PPO | 8 | 100% | Complete
Hany | Junior | 40 | 0 | 0 | 0 | 0%
Gebril | TL | 40 | 0 | 0 | 0 | 0%
PROJECT PORTFOLIO STATUS
Project | Task Hrs Est | Task Hrs Done | Completion % | Tasks | Status |  |  |  | TASK STATUS SUMMARY
CST | 71 | 46 | 64.79% | 3/9 | At Risk |  |  |  | Status | Count
FRA | 0 | 0 | 0% | 0/0 | No Tasks |  |  |  | Done | 4
PPO | 8 | 8 | 100% | 1/1 | Complete |  |  |  | In Progress | 2
[9 empty] | Backlog | 4
[9 empty] | Cancelled | 0
PROJECT COMPLETION
[9 empty] | Project | Completion %
[9 empty] | CST | 64.79%
[9 empty] | FRA | 0%
[9 empty] | PPO | 100%
RESOURCE HOURS BREAKDOWN
[9 empty] | Resource | Project Hrs | Active Task Hrs | Total
[9 empty] | Basel | 0 | 0 | 0
[9 empty] | Belal | 0 | 8 | 8
[9 empty] | Mahmoud | 0 | 3 | 3
[9 empty] | Hany | 0 | 0 | 0
[9 empty] | Gebril | 0 | 0 | 0
TASKS BY PROJECT
[9 empty] | Project | Done | In Progress | Backlog
[9 empty] | CST | 3 | 2 | 4
[9 empty] | FRA | 0 | 0 | 0
[9 empty] | PPO | 1 | 0 | 0
TASK DETAILS - QUICK VIEW
Task ID | Project | Task Name | Status | Est Hrs | Actual Hrs | Resource | Due Date
TSK-001 | PRJ-001 | Mobile View Testing Cycle | Done | 40 | 36 | Mahmoud, Hany | 2026-01-15
TSK-002 | PRJ-001 | حذف اسم المفوض | Done | 12 | 8 | Belal, Hany | 2026-01-11
TSK-003 | PRJ-001 | missing punch updates | In Progress | 3 | 0 | Mahmoud | 2026-01-15
TSK-004 | PRJ-001 | إجازة متعاقدين | Backlog | 0 | 0
TSK-005 | PRJ-001 | إشعارات + تقرير تعليم الأبناء | In Progress | 8 | 0 | Belal | 2026-01-15
TSK-006 | PRJ-001 | إشعارات السحب الطلب | Done | 8 | 2 | Belal | 2026-01-11
TSK-007 | PRJ-001 | طلب خارج الدوام متعقدين طلب دفع خارج الدوام متعقدين طلب إلغاء خارج الدوام متعقدين | Backlog | 0 | 0 |  | 2026-01-26
TSK-008 | PRJ-003 | Portal ¦ Law Services Testing Cycle | Done | 8 | 8 | Gebril | 2026-01-13
TSK-009 | PRJ-001 | عدم الاستفادة من الخدمات | Backlog | 0 | 0
TSk-010 | PRJ-001 | خدمة إلغاء سلفة شخصية (سداد مبكر) | Backlog | 0 | 0 |  | 2026-01-28
TASK SUMMARY METRICS
Total Tasks: | 10
Tasks Done: | 4
Tasks In Progress: | 2
Tasks In Backlog: | 4
Overall Completion Rate: | 40%
Total Estimated Hours: | 79
Total Actual Hours: | 54
Total Hours Variance: | -25

## Projects
PROJECT PORTFOLIO - TASK-DRIVEN TRACKING
Projects are containers that aggregate their tasks. All hours and completion calculated from Tasks sheet.
Project ID | Project Name | Total Weight | Task Hrs Est | Task Hrs Actual | Task Hrs Done | Completion % | Tasks Done | Tasks Total | Status | Priority | Start Date | Target Date
PRJ-001 | CST | 1 | 71 | 46 | 46 | 64.79% | 3 | 9 | At Risk | 2026-01-01 | 2026-01-09 21:00 | 2026-03-15
PRJ-002 | FRA | 1 | 0 | 0 | 0 | 0% | 0 | 0 | No Tasks | 2026-01-01 | 2026-01-01
PRJ-003 | PPO | 1 | 8 | 8 | 8 | 100% | 1 | 1 | Complete | 2026-01-12 | 2026-01-13 | 13-01-2025
[13 empty] | Projects Total Hours | 71
[13 empty] | Avg.Completion | 54.93%
Formulas:
Start Date = [Priority]+[Task Hrs Est]/8

## Assumptions
QC SCENARIO PLANNING - ASSUMPTIONS
RESOURCE PRODUCTIVITY RATES
Resource Level | Project Rate (%/hr) | Task Rate (%/hr)
Senior QC | 3% | 6%
Mid QC | 2% | 4%
Junior QC | 1% | 2%
TL | 5% | 10%
PROJECT WEIGHT DISTRIBUTION
Resource Level | Weight Fill % | Description
Senior QC | 70% | Senior fills 70% of project weight
Mid QC | 50% | Mid fills 50% of project weight
Junior QC | 30% | Junior fills 30% of project weight
TL | 90% | TL fills 90% of project weight
WORKING HOURS ASSUMPTIONS
Hours per Day | 8
Working Days per Week | 5

## Resources
QC RESOURCES
Resource Name | Level | Hourly Rate ($) | Project Rate (%/hr) | Task Rate (%/hr) | Weight Fill | Availability (hrs/week)
Gebril | TL | 85 | 5% | 10% | 90% | 40
Basel | Senior | 85 | 3% | 6% | 70% | 40
Belal | Mid | 65 | 2% | 4% | 50% | 40
Mahmoud | Junior | 45 | 1% | 2% | 30% | 40
Hany | Junior | 45 | 1% | 2% | 30% | 40
TEAM SUMMARY
Total Team Size: | 5
Total Weekly Hours: | 160
Average Hourly Rate: | 60

## Tasks
DYNAMIC TASK MANAGEMENT - STATUS & PERFORMANCE TRACKING
Track task status (Backlog/In Progress/Done), actual hours, and performance. Only ACTIVE tasks count toward utilization.
Task ID | Project ID | Task Name | Status | Required Hours | Days | Resource 1 | R1 Est Hrs | R1 Actual Hrs | Resource 2 | R2 Est Hrs | R2 Actual Hrs | Total Est | Total Actual | Est Completion | Actual Completion | Hours Variance | Efficiency % | Start Date | Due Date | Completed Date | Priority | Dependencies | TASK SUMMARY
TSK-001 | PRJ-001 | Mobile View Testing Cycle | Done | 32 | 4 | Mahmoud | 20 | 16 | Hany | 20 | 20 | 40 | 36 | 125% | 112.5% | -4 | 111.1% | 2026-01-11 | 2026-01-15 | 2026-01-13 | Medium | None | Total Tasks: | 10 | HOW IT WORKS:
TSK-002 | PRJ-001 | حذف اسم المفوض | Done | 8 | 1 | Belal | 8 | 2 | Hany | 4 | 4 | 12 | 8 | 150% | 100% | -4 | 150% | 2026-01-11 | 2026-01-11 | 2026-01-11 | Medium | None | Total Required Hours: | 240 | Required Hours = Total work needed (e.g., 24 hrs = 3 days)
TSK-003 | PRJ-001 | missing punch updates | In Progress | 2 | 0.25 | Mahmoud | 3 |  |  |  |  | 3 | 0 | 150% | 0% | -3 | 0% | 2026-01-15 | 2026-01-15 |  | High | None | Total Allocated Hours: | 79 | Allocated Hours = Sum of hours from Resource 1 + Resource 2
TSK-004 | PRJ-001 | إجازة متعاقدين | Backlog | 16 | 2 | [6 empty] | 0 | 0 | 0% | 0% | 0 | 0% |  |  |  | High | None | Average Completion: | 84.38% | Completion % = Allocated / Required (100% = done)
TSK-005 | PRJ-001 | إشعارات + تقرير تعليم الأبناء | In Progress | 8 | 1 | Belal | 8 |  |  |  |  | 8 | 0 | 100% | 0% | -8 | 0% | 2026-01-15 | 2026-01-15 |  | High | None | Tasks Complete: | 4 | Hours Remaining = Required - Allocated (negative = surplus)
TSK-006 | PRJ-001 | إشعارات السحب الطلب | Done | 8 | 1 | Belal | 8 | 2 |  |  |  | 8 | 2 | 100% | 25% | -6 | 400% | 2026-01-11 | 2026-01-11 | 2026-01-11 | Medium | None | Tasks Cancel: | 0 | Days = Required Hours / 8 (from Assumptions)
TSK-007 | PRJ-001 | طلب خارج الدوام متعقدين طلب دفع خارج الدوام متعقدين طلب إلغاء خارج الدوام متعقدين | Backlog | 42 | 5.25 | [6 empty] | 0 | 0 | 0% | 0% | 0 | 0% | 2026-01-12 | 2026-01-26 |  | Critical | None | Task Active: | 2
TSK-008 | PRJ-003 | Portal ¦ Law Services Testing Cycle | Done | 16 | 2 | Gebril | 8 | 8 |  |  |  | 8 | 8 | 50% | 50% | 0 | 100% | 2026-01-12 | 2026-01-13 | 2026-01-12 | Critical | None
TSK-009 | PRJ-001 | عدم الاستفادة من الخدمات | Backlog | 80 | 10 | [6 empty] | 0 | 0 |  |  | 0 | 0% |  |  |  | Critical | None
TSk-010 | PRJ-001 | خدمة إلغاء سلفة شخصية (سداد مبكر) | Backlog | 28 | 3.5 | [6 empty] | 0 | 0 |  |  | 0 | 0% | 2026-01-22 | 2026-01-28 |  | High | None
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
[5 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0%
0
0
0